## Sheet1
Product Backlog | Sprint Backlog | Duration of Sprint | Scrum Artifacts
Requirements/User Stories | Individual Tasks |  | Burndown Chart/Scrumboard
1. Allow Manager User to login, register an email, change and reset password | 1.1 Kyle - Build Templates, Views, and URLs for the home page, login page, register page, change password page, and reset password page. | 2 Days
1.2 Ray - Build Model for user, to include _id, Name, and Email
1.3 Miles - Create Navagation between all logged out pages.
2. Allow Manager to create a New Project, add a Title, and a graphic to it. Allow the Manager to navigate to a separate page to view previously created Projects. | 2.1 Kyle - Build Templates, Views, and URLs for a Project Creation page and Display Projects page, displaying the title and graphic | 2 Days
2.2 Ray - Build Model for Project, to include _id, Title, Image
2.3 Miles- Create the navigation between the different account tiers
3. Allow Manager to create Tasks within each Project, and assign them a Title, description, due date, est hours, current status symbol, and commentary | 3.1 Ray - Create Task model, to include _id(or ticket #), Task Title, task description, Task creator, DevOp taking on the ticket, status, and commentary. | 2 Days
3.2 Kyle - Build template, view, & urlpattern inside Project view to show all Project tasks. Should display everything listed in the model, as well as a button to create a new task.
| 3.3 Kyle & Ray - Ensure all tests are passing for views, templates, models, URLs, reverse lookups, and models. All users can view all current projects, and all tasks within each project. | Deadline Tuesday, April 10th
3.4 Miles - Help with models to make sure they will add corespopnding data to "Doughnut graphs"
4. Follow templates with styling. Bootstrap and Css classes. | 4.1 Miles - Follow template creations to add styling. | April 10th